## SampleWorkPlan
Sample Project Workplan | Sample Project Workplan
Objectives | Deliverables |  | Deliverable Units | Description
Streambank & Riparian Restoration | Publish RFPs | 1 | RFPs | Contract to regrade 1000 ln ft of Kanawha streambank between river mile 34 and 35 and plant trees to cover 3 acres of the riparian corridor.'
| Execute Feasibility Planning or Design Contracts | 1 | Contracts
| Develop Project Plans or Design Documents | 1 | Plans
| Execute Construction Contract(s) | 2 | Contracts
| Restore Streambank By Recontouring or Regrading | 1000 | Linear Feet
| Plant Trees in Riparian Areas | 100 | Trees
| Plant Trees in Riparian Areas | 3 | Acres
Stream Restoration | Publish RFPs | 1 | RFPs
| Develop Project Plans or Design Documents | 1 | Plans
| Restore Stream Channel | 1000 | Linear Feet
| Install In-Stream Habitat Structures | 4 | Structures
| Restore Natural Flow | 1000 | Linear Feet
Dam Modification or Removal | Publish RFPs | 1 | RFPs | Contract to remove dam on Olentangy River at 5th Avenue and remove and dispose of all support structures and demolition debris.
| Execute Feasibility Planning or Design Contracts | 1 | Contracts
| Remove Dams | 1 | Dams
| Remove Associated Dam Support Structures | 4 | Structures
| Restore Natural Flow | 1000 | Linear Feet
| Dispose of Demolition Debris | 500 | Cubic Yards
Education & Outreach | Develop Brochures/Fact Sheets | 5 | Brochures/Fact Sheets | Develop 5 fact sheets at different stages of the project ot inform public about dam removal progress and mail each to 5,000 homes. Hold 2 public meetings before dam removal to collect and respond to public comments. Develop press releases before and after dam removal for print and broadcast media. Install signs on each side of the river discussing the project and the environmental improvements.
| Solicit Public Input | 2 | Public Meetings
| Develop Press Releases | 2 | Press Releases
| Install Signs | 2 | Signs
| Develop Model Ordinances |  | Ordinances
Pre- and Post-Implementation Monitoring | Prepare Quality Assurance Plan | 1 | QAPP
| Conduct Chemical Sampling | 5 | Sites
| Conduct Habitat (QHEI or HHEI) Sampling | 2 | Sites
| Prepare and Submit Final Monitoring Report and Data | 1 | Report
| Reduce Sediment Loadings | 1000 | Tons/Year
| Reduce Nitrogen Loadings | 1000 | Pounds/Year

## SampleProgress
Sample Progress Report
Objectives | Deliverables |  | Deliverable Units | Progress thru Last Report | Progress this Report Period | Total | % Complete | Comments
Streambank & Riparian Restoration | Publish RFPs | 1 | RFPs | 1 |  | 1 | 100% | Delayed 3 months due to rebidding contract for grading work. Contractor hired and work has begun.
| Execute Feasibility Planning or Design Contracts | 1 | Contracts | 1 |  | 1 | 100%
| Develop Project Plans or Design Documents | 1 | Plans | 1 |  | 1 | 100%
| Execute Construction Contract(s) | 2 | Contracts | 1 | 1 | 2 | 100%
| Restore Streambank By Recontouring or Regrading | 1000 | Linear Feet | 0 | 500 | 500 | 50%
| Plant Trees in Riparian Areas | 100 | Trees | 0 |  | 0 | 0%
| Plant Trees in Riparian Areas | 3 | Acres | 0 | 0 | 0 | 0%
Stream Restoration | Publish RFPs | 1 | RFPs | 1 |  | 1 | 100% | Will be completed after grading work is finished.
| Develop Project Plans or Design Documents | 1 | Plans | 1 |  | 1 | 100%
| Execute Construction Contract(s) |  | Contract | 1 | 1 | 2
| Restore Flood Plain | 1000 | Linear Feet | 200 | 500 | 700 | 70%
| Restore Stream Channel | 1000 | Linear Feet | 0 | 500 | 500 | 50%
| Install In-Stream Habitat Structures | 4 | Structures | 0 |  | 0 | 0%
| Restore Natural Flow | 1000 | Linear Feet | 0 | 0 | 0 | 0%
Dam Modification or Removal | Publish RFPs | 1 | RFPs | 1 | 0 | 1 | 1 | Contract to remove dam on Olentangy River at 5th Avenue and remove and dispose of all support structures and demolition debris.
| Execute Feasibility Planning or Design Contracts | 1 | Contracts | 1 | 0 | 1 | 1
| Develop Project Plans or Design Documents |  | Plans |  |  | 0
| Execute Contract(s) |  | Contract |  |  | 0
| Remove Dams | 1 | Dams | 1 | 0 | 1
| Modify Dams |  | Dams |  |  | 0
| Remove Associated Dam Support Structures | 4 | Structures | 4 | 0 | 4
| Install Fish Passage and/or Habitat Structures |  | Structures |  |  | 0
| Restore Natural Flow | 1000 | 500 | 1000 | 0 | 1000
| Dispose of Demolition Debris | 500 | Cubic Yards | 500 | 0 | 500
Education & Outreach | Develop Brochures/Fact Sheets | 5 | Brochures/Fact Sheets | 2 | 1 | 3 |  | Develop 5 fact sheets at different stages of the project ot inform public about dam removal progress and mail each to 5,000 homes. Hold 2 public meetings before dam removal to collect and respond to public comments. Develop press releases before and after work is complete. Install temporary signs on each side of the stream to describe purpose of work. Replace temporary signs with permanent signs describing environmental benefits of the dam removal after all work is complete.
| Solicit Public Input | 2 | Public Meetings | 2 | 0 | 2
| Develop Press Releases | 2 | Press Releases | 1 | 0 | 1
| Install Signs | 4 | Signs | 2 | 0 | 2
Pre- and Post-Implementation Monitoring | Prepare Quality Assurance Plan | 1 | QAPP | 1 | 0 | 1
| Conduct Chemical Sampling | 6 | Sites | 3 | 0 | 3
| Conduct Habitat (QHEI or HHEI) Sampling | 2 | Sites | 1 | 0 | 1
| Prepare and Submit Final Monitoring Report and Data | 1 | Report | 0 | 0 | 0
| Reduce Sediment Loadings | 1000 | Tons/Year | 0 | 0 | 0
| Reduce Nitrogen Loadings | 1000 | Pounds/Year | 0 | 0 | 0

## Deliv&MilestoneUnits
Watershed: |  | HUC:
Subwatershed: |  | HUC:
Subwatershed Acreage:
Objectives | Deliverables | Deliverable Units | Description | TARGET | COSTS
Streambank & Riparian Restoration | Restore Streambank Using Bio-Engineering | Linear Feet
| Restore Streambank By Recontouring or Regrading | Linear Feet
| Plant Grasses in Riparian Areas | Acres
| Plant Prairie Grasses in Riparian Areas | Acres
| Remove/treat Invasive Species | Acres
| Plant Trees or Shrubs in Riparian Areas | Trees
| Plant Trees or Shrubs in Riparian Areas | Acres
Stream Restoration | Restore Flood Plain | Linear Feet
| Restore Stream Channel | Linear Feet
| Install In-Stream Habitat Structures | Structures
| Install Grade Structures | Structures
| Construct 2-Stage Channel | Linear Feet
| Restore Natural Flow | Linear Feet
Wetland Restoration | Reconnect wetland to stream | Acres
| Reconstruct & Restore Wetlands | Acres
| Plant Wetland Species | Acres
Dam Modification or Removal | Remove Dams | Dams
| Modify Dams | Dams
| Install Fish Passage and/or Habitat Structures | Structures
| Restore Natural Flow | Linear Feet
Levee or Dike Modification or Removal | Remove Levees | Levees
| Breach or Modify Levees | Levees
| Remove Dikes | Dikes
| Modify Dikes | Dikes
| Restore Natural Flood Plain Function | Acres
Acid Mine Drainage & AML Reclamation | Construct Lime Dosers | Dosers
| Install Slag Leach Beds | Beds
| Install Limestone Leach Beds | Beds
| Install Limestone Channels | Linear Feet
| Repair Subsidence Sites | Acres
| Reclaim Abandoned Mine Land | Acres
| Reclaim Pit Impoundments | Acres
| Install Successive Alkalinity Producing Systems | SAPS
| Cover Toxic Mine Spoils | Acres
| Construct Acid Mine Drainage Wetland | Acres
Conservation Easements | Acquire Riparian Conservation Easements | Acres
| Acquire Wetland Conservation Easements | Acres
Home Sewage Treatment Systems | Inspect HSTS | Inspections
| Repair or Replace Traditional HSTS | HSTS
| Repair or Replace Alternative HSTS | HSTS
Agricultural Best Management Practices | Plant Cover/Manure Crops | Acres
| Critical Area Planting | Acres
| Install Conservation Cover | Acres
| Install Field Borders | Acres
| Install Nitrogen Reduction Practices | Acres
| Install Controlled Drainage Structures | Structures
| Install Controll Drainage System | Acres
| Implement Contour Buffer Strips | Acres
| Implement Contour Buffer Farming Practices | Acres
| Develop Nutrient Management Plans | Acres
| Develop Whole Farm Management Plans | Acres
| Implement Conservation Tillage Practices | Acres
| Implement Prescribed & Conservation Grazing Practices | Acres
| Install Alternative Water Supplies | Supplies
| Install Erosion & Sediment Control Structures | Structures
| Construct 2-Stage Channel | Linear Feet
| Install Grassed Waterways | Acres
| Install Vegetated Buffer Strips | Linear Feet
| Install Livestock Crossings | Crossings
| Install Heavy Use Feeding Pads | Pads
| Install Livestock Exclusion Fencing | Linear Feet
| Install Chemical Mixing Pads | Pads
| Construct Animal Waste Storage Structures | Structures
| Implement Manure Management Practices | Acres
| Conduct Soil Testing | Tests
| Implement Grass/Legume Rotations | Acres
| Install Grass Manure Spreading Strips | Acres
| Implement Manure Transfer Practices | Acres
| Implement Drainage Water Management Practices | Acres
| Install Roof Water Management Practices | Practices
Education & Outreach | Develop Brochures/Fact Sheets | Brochures/Fact Sheets
| Conduct Watershed Festivals | Festivals
| Conduct Public Meeting | Public Meetings
| Develop Press Releases | Press Releases
| Create/Maintain Websites | Website
| Install Signs | Signs
| Develop Displays | Displays
| Conduct Tours | Tours
| Conduct Tours via Canoe | Canoe Trips
| Conduct Stream Clean-Ups | Clean-Ups
| Conduct Field Days | Days
| Stencil Storm Drains | Drains
| Conduct Workshops | Workshops
| Conduct Training | Training Sessions
| Develop Manual(s) | Manuals
| Provide Technical Assistance to Group(s) | Groups
| Deliver On-Site Technical Assistance | Site Visits
| Develop Model Ordinances | Ordinances
| Develop Newsletters | Newsletters
Urban/Suburban Runoff Management Practices | Rain Gardens/Bioretention/Bioinfiltration | Gallons (storage capacity)
| Vegetated Swales | Linear Feet
| Planter Boxes | Gallons (storage capacity)
| Green Roofs | Square Feet
| Permeable Pavement | Sq. Feet / Gallons (storage capacity in sub-base)
| Constructed wetland for stormwater management | Acres
Urban/Suburban Stormwater Control Measures | Street Sweeping | Frequency
| Pollution Prevention at Municipal Faclities/Operations | Number of Operations
| Manage Pesticides and Fertilizer at Parks and Golf Courses | Acres
| Implement Stormwater Ordinance | Ordinances
| Illicit Discharge Detection and Elimination | Number of Checks during Dry Weather; Number of Site Inspections
| Runoff Controls at Construction Sites | Number of Site Inspections
| Monitoring of Stormwater Management Practices | Number of Monitoring Sites
| Measurement of Stream Channel Erosion | Number of Monitoring Sites
| Monitoring of Effects of Stormwater Program (In-stream Water Quality Monitoring) | Number of Monitoring Sites; Number of Monitoring Events; Number of Parameters
Other Actions